|  | Go-Live Readiness Criteria Health-Chex, LLC · Consulting & Training |
| --- | --- |

Decide with evidence, not with optimism

Most go/no-go meetings fail the same way: the criteria were never written down, so the conversation becomes a contest of confidence between the people who want to go and the people who are nervous. This worksheet forces the criteria into the open before the meeting, keeps the go/no-go decision separate from the fix list, and makes every claim something a person could check and record as failed. Complete the header once, then one row per function.

DECISION — COMPLETE ONCE

| Organization / project | Planned go-live date | Go / no-go meeting Far enough ahead that "no" is still affordable — usually 5 to 7 days out. |
| --- | --- | --- |
| Who makes the call One named person, not a committee | Who must be in the room | What "no-go" means in practice Delay to what date — and what happens to the people already scheduled |
| Last date a delay can be called After this, stopping costs more than going | Who tells the staff | Rollback plan tested? Y / N — who tested it, when |

CRITERIA — ONE ROW PER FUNCTION

| Function or area | Claim that must be true | Evidence, and who verifies it | Verified | Weight |
| --- | --- | --- | --- | --- |

|  | Only three weights, and only one of them stops a go-live. A Blocker is a claim that, if false, means patients or revenue are harmed on day one — and it stops the go-live on its own, without debate. A Should-fix goes on the fix list with an owner and a date. A Watch you look at in week one. If more than a fifth of your rows are Blockers, they are not all blockers — and the ones that aren't teach everybody that the word means nothing. |
| --- | --- |

WORKED EXAMPLE — THREE ROWS FILLED IN

| Function or area | Claim that must be true | Evidence, and who verifies it | Verified | Weight |
| --- | --- | --- | --- | --- |
| Pharmacy | Every order in the top-20 formulary list transmits to the dispensing system and returns a confirmation within 60 seconds, including the three that require a weight-based dose. | Pharmacy lead runs all 20 in the mirrored environment and keeps the log. Named: not "pharmacy." |  | Blocker — a silent failure here reaches a patient |
| Registration | A walk-in with no referral can be registered and routed without a workaround, by a clerk who has not been shown how that morning. | Observed on two clerks by the trainer, using the go-live build, not the training build. |  | Blocker — it happens on day one, every site |
| Billing | A claim generated from a day-one encounter passes the clearinghouse edit check. | Revenue cycle manager submits three test claims and reports the rejections. |  | Should-fix — painful, but it surfaces in week two, not hour one |

|  | Notice what the claims have in common. Each one names a condition and a person, and each one could come back false. "Pharmacy is ready" cannot come back false — there is no observation that would contradict it, which is why it always gets a yes. The claim in the first row can fail on a Tuesday afternoon with a log to prove it, which is the entire point. |
| --- | --- |

FIX LIST — KEPT SEPARATE FROM THE DECISION

| Issue | Weight | Owner | Due | Workaround if not fixed by go-live |
| --- | --- | --- | --- | --- |

THE DECISION

| Decision Go · Go with conditions · No-go | If "go with conditions" — the conditions, and who owns each | Decided by / date |
| --- | --- | --- |

HOW TO USE THIS

- Write the criteria before the meeting, not in it. Criteria invented live get negotiated live. Circulate them a week ahead and let people argue about the wording while it is still cheap.

- Every claim must be able to come back false. "Pharmacy is ready" cannot. "All 20 top-formulary orders return a confirmation within 60 seconds" can. If no observation would contradict it, it is not a criterion.

- Name a person for the evidence, not a department. "The team verified it" is how something goes unverified by everyone.

- Keep the fix list out of the decision. Deciding whether to go and deciding what to fix are two different conversations, and merging them is how a room talks itself into going.

- Set the last date a delay can be called — in advance. After that point you are going live regardless, so everyone should know when it passes.

|  | A readiness review before your go/no-go meeting. Send us your criteria as they stand and we will read them against the failure modes above — which claims cannot fail, which blockers are not really blockers, and which function nobody has written a row for. We will write back before your meeting. No charge, and no obligation after it. info@health-chex.com |
| --- | --- |

Health-Chex, LLC · Charlotte, NC · health-chex.com · Checkpoint, our monthly newsletter